## terms
| short name | description | Accomplishments | Targets | Finance | Re-balancing
1 | diagnose problems | Assist regional coordinators and project leaders diagnose data management problems and develop strategies for research data management | 1.up-to-dateness (traditional db's) 2.linkage(meta-data) 3.Suitable for new projects | Existing data?
2 | design strategies | Develop and agree on approaches, timescales, deliverables for implementing these strategies | ?? | rapid-gropu knowledge acquisition
3 | implement plans | Lead the implementation of these strategies through development of solutions to specific problems, training and technical support, working in the regions as required | Project synthesis using a spiral approach | plan better
4 | synthesize experiences | Working with suitable partners to develop generic data management solutions to cope with emerging problems identified by Theme leaders and Unit heads | Logbook-project. GPG | publish/dissemination (feeding back to diagnose problems)
5 | feedback/disseminate lessons/informing policy | Ensuring that research data management strategies are consistent with and reinforce wider knowledge management strategies for ICRAF | DM policy developed (from lessons). Recognize other policy series. Has not been consulted widely. Needs to, since projects from which lessons are drawn were not many) | consultations
Note on B6: Not very clear what is intended by this item in the terms of reference?? But my guess….

## accomplish
The spiral approach touched on all the terms but to varying degrees, so this table (useful for reporting) does not represent what we actually did. It is artificial! | [8 empty] | Score
desperation | experience | diagnose problems | catalogued symptoms from individual case studies | hypothesized the underlying problems: too much in one go! |  |  |  |  | 80%
hope | experience | design strategies | Characterized data extraction activities | Refined the extraction process by identifying hidden states (eg. integration) and activities (meta-data capture) which were not obvious) |  |  |  |  | 80%
| experience | implement plans (where?) | ASB | Transvic | ECA | SA | SEA | next:AHT, SALWA. LA | 50%
| principles | synthesize experiences | Conceptualized DM as a complex 4-state system | Helped to define custom-solutions for specific problems. Backbone to my consultancy services. Less and less from ICRAF. Still takes 40% of my time. MDG, LAB, Safeguard, PPA-iv | Derived a generic institute-level data integrator using file properties | GPG | New projects are built from old data! So, new method will halt further decline but (1) will take long to provide positive feedback (2) not applicable to old data. Ned for rapid DIK |  | 75%
direction | refinement | feedback/disseminate lessons (to who?) | to management: compile ASB+ICRAF policy. Still not enforceable because it is narrow | to other scientist: who request for help (what about others out of reach. Flaw: feedback does not reach original source) | opportunity for DDG-P: integrate plan-execute-report | Well attended seminars |  |  | 75%
symptoms
When data ara handed in (P. Smithson)
When old staff leaves (Andreas, Bashir, Amadou, Kwesiga)
When new staff arrives (what data do you have on …)
When Jan Larman wants WB indicators (whole institution grinds to a halt)
When some evaluation is looming
When a dataset is complex