DRAFT

Programme of Work 2008 – Research Methods Group

(Work Area – Data Management)

CGIAR Alignment Proposal – Action relating to the ‘Data Management’ issues of the group

(Amended according to 2008 application – RMGAlignmentProposal-WkAreas&Activities_Sept07.doc)

| ACTION |  | Milestone for the end of 2007 | Milestone for the end of 2008 | Milestone for the end of 2009 |
| --- | --- | --- | --- | --- |
| Design and implement research data management strategies |  | Aligned data management policies adopted in both ILRI and ICRAF | Priority projects in ICRAF and ILRI fully implementing data management policies | ESA MTP projects using best practice for research data management |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| Research data management | Workshops, travel, consultants | $25,000 | Staff time and other costs | $84,000 |

Strategy & Objectives of the RMG that relate to the ‘Data Management’ issues of the group

(Blue text – added after Dec 2007 review and planning meeting)

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Research data management | - Value of research data limited by not maintaining high quality archives - Inefficient data processing due to poor understanding of management needs - Data and other research documents not linked - Data vulnerable due to poor documentation, inadequate backup, few people who know about any dataset,… - Projects with multiple partners often have no clear data ownership and sharing policy - Technical tools to help in RDM not known or adopted - All the above compounded by distributed research sites and teams - good and bad RDM practice within ILRI/ICRAF groups is hidden - large backlog of data - fraud is hardly talked about | - Develop aligned data management, ownership and access policies - Assist all projects with integrated data management strategies that meet immediate and long term needs - Provide tools and approaches to help technicians, scientists and managers assess and improve their data management - Help centres establish and maintain long term research data archives - Build mechanisms for allowing outreach scientists to be fully integrated into data management practice - Create means of monitoring use of our data and getting feedback |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| RDM (Alignment activities) | Design and implement research data management strategies | - Revised version of RDM policy produced incorporating inputs from ILRI/ICRAF staff. Sent to management for ratification. - Final version incorporated onto RMG website and widely circulated. |  |  |
|  | Technical implementation of developed policies & practices | - Recruitment of Data Archivist (x 2) - Archiving (Data Publisher) tools & support in place. - Training course for Data Publisher (1 day) - Practical guide for Data Originators produced & circulated. - Workshop for trainers in data archiving who will be the key resource people (1 day)??? - Workshop for centre data curators in Nairobi (3days). - Workshop for centre data curators in Addis (3days). |  |  |
| Research Data Management | Assist all projects with integrated data management strategies that meet immediate and long term needs | - Integrated data management strategies designed & implemented for ≥ 4 research teams. |  |  |
|  | Tools and approaches to help technicians, scientists and managers assess and improve their data management | - All resources & tools on website |  |  |
|  | Help centres establish and maintain long term research data archives | Main activities under Alignment above |  |  |
|  | Create means of monitoring use of our data and getting feedback to identify emerging problems | - Use information generated during implementation of RDM policy - Activity? |  |  |
|  | Support to ILRI / ICRAF projects on database design & use | - Input into ≥ 4 projects (per location) |  |  |