## Research Methods Group – Alignment Work Areas & Activities

## Updated: 11th Sept 2007 (Jane Poole)

## Milestones for the Alignment of Research Support Services – amended from the Alignment Proposal document (Nov 2006)

| ACTION | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 | Milestone for the end of 2009 |
| --- | --- | --- | --- | --- |
| Establish Research Methods Group (RMG) | RMG established & functioning with approved strategic plan | RMG achieving milestones under 5 objectives and recognized within ILRI-ICRAF |  | RMG providing services to all partners of ESA MTP |
| Research Quality Processes |  | Aligned procedures for review and documentation produced | Aligned procedures implemented and being used effectively at ILRI and ICRAF | Common procedures adopted within ESA |
| Research methods support |  | Identify areas that need more harmonization and devise approaches to realize it | Capacity in place to provide technical support in emerging science areas needed by at least 3 project | RMG the supplier of choice for technical support in research methods among ESA projects |
| Data management strategies |  | Aligned data management policies adopted in both ILRI and ICRAF | Priority projects in ICRAF and ILRI fully implementing data management policies | ESA MTP projects using best practice for research data management |
| GIS / RS |  |  | GIS/RS service operating a single one-stop shop | Spatial analysis demands of ESA MTP projects being met |
| Research quality capacity in ESA |  | Strategy devised and funding proposals prepared |  | Funding secured and implementation started |

## N.B. Funding was received at the end of 2006, therefore Milestones achieved in 2006 were carried out without the CGIAR Contribution. Some milestones have been moved to align to the CGIAR & Centre Resource allocations.

## Detail of Activities for each ACTION

- Establish joint Research Methods Group (RMG)

| Activities | CGIAR Budget | What the cost covers | Activity Timetable |
| --- | --- | --- | --- |
| Establish the RMG and develop approved strategic plan | None |  | 2006 |
| Develop joint website - including on it a range of research methods resources and links | $9,000 | - Website developer – consultant fee - Travel costs to Ethiopia for RMG staff member to learn web design system (development & maintenance of the website) | 2007 – website design and setting-up 2008 – 2009 website development with range of resources |
| Group meetings & seminars – to share ideas, technical knowledge and to plan, monitor & evaluate the work and direction of the group | $2,000 | - Venue & catering costs of meetings – 6 in total - Publication costs for meeting outputs | All years |
| Total | $11,000 |  |  |

- Research Quality Processes - Revise research planning and implementation procedures to align across both institutes and with the needs for quality improvement

| Activities | CGIAR Budget | What the cost covers | Activity Timetable |
| --- | --- | --- | --- |
| Draft research quality procedures -based on external consultants report. Including publications and proposal reviews to ascertain current standards | None |  | 2007 |
| Implement research quality procedures | $10,000 | - Temporary database expert /programmer (1 year) to assist with additional record keeping and system requirements | 2008 |
| Facilitate workshops (Nairobi and Addis) - for ILRI and ICRAF staff to review and make operational | $3,000 | - Venue, catering & any necessary equipment costs of workshops - Travel costs to Ethiopia (2 x RMG staff) | 2008 - 2009 |
| Travel to other key ICRAF/ILRI centres (S.E.Asia, W.Africa, Asia) – same as activity above | $5,000 | - Travel costs to S.E. Asia (Indonesia), W. Africa (Mali/Cameroon) & Asia (India) | 2008 - 2009 |
| Total | $18,000 |  |  |

- Research methods support - Align current research methods across institutes, identify research methods gaps and devise approaches to fill them

| Activities | CGIAR Budget | What the cost covers | Activity Timetable |
| --- | --- | --- | --- |
| Conduct methods inventory and diagnosis work for ILRI & ICRAF (incl. Global Projects & MTP) | $4,000 | - Consultant fee (for input from regional centres & preparing a paper on latest development in research methods | 2007 |
| Produce and revise guides (& other training material) to key methods identified in previous activity | $5,000 | - Writing/editing consultant fee (to be used where necessary) - Publishing costs | All Years |
| Professional development of RMG staff - to meet some of the new challenges in emerging areas | $20,000 | - External course costs (may be on-line) - Travel costs for external courses | 2008 - 2009 |
| Total | $32,000 |  |  |

- Data management strategies - Design and implement research information and data policies and practices that maximize the long-term value of research, aligned across institutes

| Activities | CGIAR Budget | What the cost covers | Activity Timetable |
| --- | --- | --- | --- |
| Draft research information & data policies and practices – aligned across institutes (various – including RDM policy) Revised version after incorporating inputs from ILRI/ICRAF staff to be sent out to the management for ratification. | $3,000 | - Consultant fee (documentation) - Publication & dissemination costs | 2007 End Feb |
| Technical implementation of developed policies & practices 1. Archiving a. Archiving(publisher) tools in place. b. Need to develop a practical guide for the data ortiginators. 2. Quality and efficiency - tools/methods/case studies need developing | $13,000 | - Consultant fee (assistance with setting up integrated research information systems) | 2008 1b By early March 2. 2008 - 2009 |
| Facilitate workshops (Nairobi and Addis) - for ILRI and ICRAF staff to review and make operational 1. Sending out invitations for the workshops. 2. Workshop for trainers in data archiving who will be the key resource people. (1 day) 3. Workshop for all CG centers data curators in Nairobi. (3 days) 4. Workshop for CG centers in Addis for data curators. (3 days) | $3,000 | - Venue, catering & any necessary equipment costs of workshops - Travel costs to Ethiopia (2 x RMG staff) | 2008 – 2009 2008 1. 1st week of February. 2. By middle of April 3. Beginning of May 4. End of May. |
| Travel to other key ICRAF/ILRI centres (S.E.Asia, W.Africa, Asia) – same as activity above | $6,000 | - Travel costs to S.E. Asia (Indonesia), W. Africa (Mali/Cameroon) & Asia (India) | 2008 – 2009 July - August |
| Total | $25,000 |  |  |

- GIS / RS - Merge service facilities

| Activities | CGIAR Budget | What the cost covers | Activity Timetable |
| --- | --- | --- | --- |
| Joint work on CSI-Geonetwork nodes to update and harmonise inventories | $3,500 | - Temporary database assistant for (6 mths - 1 yr) | 2007 |
| Externally facilitated training workshop in spatial statistical analysis for ILRI & ICRAF spatial analysts | $5,000 | - Consultant trainer fee - Hire of venue & equipment (including temporary GIS package licenses) | 2008 |
| Commission a guide on ‘Use of spatial information in research for development planning’ | $4,500 | - Consultant fee - Publication & dissemination costs | 2008 – 2009 |
| Total | $13,000 |  |  |

- Research quality capacity in ESA – Build, encourage and support strategies to improve capacity for quality research services among partners in ESA

| Activities | CGIAR Budget | What the cost covers | Activity Timetable |
| --- | --- | --- | --- |
| Complete, publish and disseminate key paper on teaching research methods Publish the paper as a working paper. | $2,000 | - Publication & dissemination costs | 2007 – 2008 End of March. |
| Regional consultation and planning meetings and an education consultant to prepare a major proposal that will continue after end of VVOB project Continue support to partners to implement the ideas. | $40,000 | - Regional workshop & planning meetings (costs – travel, accommodation, food etc.) - Support to the regional workshop to be held in February. | 2007 – 2009 |
| Total | $42,000 |  |  |

The following table shows the proposed Alignment Budget which was sent to the CGIAR Secretariat in November 2006.  The Milestones for “Regional Quality Capacity in ESA” in the proposal document indicated activities across 2007 and 2008. However, the financial document placed the cash projection for these activities in 2008 and 2009. Consequently, the division of expenditure across work areas in 2007 was altered to reflect the need to conduct these regional capacity activities in the timeframe required to achieve the defined 2007 Milestone. The second table shows the amended yearly cash flow projections, the total for each year remains the same.

## RMG Alignment Budget (2007 – 2009) – proposal prepared Nov’ 2006

| BUDGET |  | CGIAR CONTRIBUTION |  | CENTRE CONTRIBUTION |  | Breakdown of centers contribution |  | N.B. Figures cover 3 years - except for MS1 (only 2007) |  |  |  |  |  | FUNDING FROM THE SECRETARIAT- Cash flow projection |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FUNDING REQUEST | Nature | Detail ($) | Summary | Detail ($) (rounded figure) | Summary | Center staff time ($) | Center non-staff costs | Staff time | Ave. daily rate ($) | # days | # per-sons | Sub-Total ($) | Total ($) | 2007 ($) | 2008 ($) | 2009 ($) |
| RMG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish RMG | Meetings, website, | 11,000 |  | 89,000 |  | 89,412 | None | DG | 1,300 | 1 | 2 | 2,600 |  | 3,667 | 3,667 | 3,667 |
|  |  |  |  |  |  |  |  | Board | 350 | 0.2 | 5 | 350 |  |  |  |  |
|  |  |  |  |  |  |  |  | DDG | 650 | 30 | 2 | 39,000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Head RMG | 650 | 24 | 1 | 15,600 |  |  |  |  |
|  |  |  |  |  |  |  |  | Ass. Head | 400 | 20 | 1 | 8,000 |  |  |  |  |
|  |  |  |  |  |  |  |  | All RMG | 200 | 12 | 10 | 24,000 | 89,550 |  |  |  |
| Research quality processes | Meetings, travel | 18,000 |  | 62,000 |  | 62,000 | None | Head RMG | 650 | 72 | 1 | 46,800 |  | 6,000 | 6,000 | 6,000 |
|  |  |  |  |  |  |  |  | Ass. Head | 400 | 36 | 1 | 14,400 | 61,200 |  |  |  |
| Research Methods Support | Publishing, staff develop-ment | 32,000 |  | 42,000 |  | 42,000 | None | Head RMG | 650 | 36 | 1 | 23,400 |  | 10,667 | 10,667 | 10,667 |
|  |  |  |  |  |  |  |  | Ass. Head | 400 | 36 | 1 | 14,400 |  |  |  |  |
|  |  |  |  |  |  |  |  | Other RMG | 200 | 6 | 5 | 6,000 | 43,800 |  |  |  |
| Data management strategies | Workshops, travel, consultants | 25,000 |  | 84,000 |  | 84,000 | None | DM Specialist | 330 | 108 | 1 | 35,640 |  | 8,333 | 8,333 | 8,333 |
|  |  |  |  |  |  |  |  | Other RMG | 200 | 36 | 6 | 43,200 | 78,840 |  |  |  |
| GIS/RS | Technical assistance, guide, workshop | 13,000 |  | 21,000 |  | 21,000 | None | GIS Specialists | 250 | 42 | 2 | 21,000 | 21,000 | 6,500 | 6,500 | - |
| Research quality capacity in ESA | Publishing, workshops | 42,000 |  | 54,000 |  | 53,500 | None | Training Specialist | 400 | 60 | 1 | 24,000 |  |  | 21,000 | 21,000 |
|  |  |  |  |  |  |  |  | Head RMG | 650 | 20 | 1 | 13,000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Other RMG | 200 | 20 | 4 | 16,000 | 53,000 |  |  |  |
|  | TOTAL | 141,000 |  | 352,000 |  | 351,912 |  |  |  |  |  |  | 347,390 | 35,167 | 56,167 | 49,667 |

RMG Alignment Budget (2007 – 2009) – Requested amendment (N.B. Totals for each year remain the same)

| BUDGET |  | CGIAR CONTRIBUTION |  | CENTRE CONTRIBUTION |  | Breakdown of centers contribution |  | N.B. Figures cover 3 years - except for MS1 (only 2007) |  |  |  |  |  | FUNDING FROM THE SECRETARIAT- Cash flow projection |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FUNDING REQUEST | Nature | Detail ($) | Summary | Detail ($) (rounded figure) | Summary | Center staff time ($) | Center non-staff costs | Staff time | Ave. daily rate ($) | # days | # per-sons | Sub-Total ($) | Total ($) | 2007 ($) | 2008 ($) | 2009 ($) |
| RMG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish RMG | Meetings, website, | 11,000 |  | 89,000 |  | 89,412 | None | DG | 1,300 | 1 | 2 | 2,600 |  | 3,667 | 3,667 | 3,667 |
|  |  |  |  |  |  |  |  | Board | 350 | 0.2 | 5 | 350 |  |  |  |  |
|  |  |  |  |  |  |  |  | DDG | 650 | 30 | 2 | 39,000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Head RMG | 650 | 24 | 1 | 15,600 |  |  |  |  |
|  |  |  |  |  |  |  |  | Ass. Head | 400 | 20 | 1 | 8,000 |  |  |  |  |
|  |  |  |  |  |  |  |  | All RMG | 200 | 12 | 10 | 24,000 | 89,550 |  |  |  |
| Research quality processes | Meetings, travel | 18,000 |  | 62,000 |  | 62,000 | None | Head RMG | 650 | 72 | 1 | 46,800 |  |  | 10,000 | 8,000 |
|  |  |  |  |  |  |  |  | Ass. Head | 400 | 36 | 1 | 14,400 | 61,200 |  |  |  |
| Research Methods Support | Publishing, staff develop-ment | 32,000 |  | 42,000 |  | 42,000 | None | Head RMG | 650 | 36 | 1 | 23,400 |  | 4,000 | 14,000 | 14,000 |
|  |  |  |  |  |  |  |  | Ass. Head | 400 | 36 | 1 | 14,400 |  |  |  |  |
|  |  |  |  |  |  |  |  | Other RMG | 200 | 6 | 5 | 6,000 | 43,800 |  |  |  |
| Data management strategies | Workshops, travel, consultants | 25,000 |  | 84,000 |  | 84,000 | None | DM Specialist | 330 | 108 | 1 | 35,640 |  | 3,000 | 12,000 | 10,000 |
|  |  |  |  |  |  |  |  | Other RMG | 200 | 36 | 6 | 43,200 | 78,840 |  |  |  |
| GIS/RS | Technical assistance, guide, workshop | 13,000 |  | 21,000 |  | 21,000 | None | GIS Specialists | 250 | 42 | 2 | 21,000 | 21,000 | 3,500 | 6,000 | 3,500 |
| Research quality capacity in ESA | Publishing, workshops | 42,000 |  | 54,000 |  | 53,500 | None | Training Specialist | 400 | 60 | 1 | 24,000 |  | 21,000 | 10,500 | 10,500 |
|  |  |  |  |  |  |  |  | Head RMG | 650 | 20 | 1 | 13,000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Other RMG | 200 | 20 | 4 | 16,000 | 53,000 |  |  |  |
|  | TOTAL | 141,000 |  | 352,000 |  | 351,912 |  |  |  |  |  |  | 347,390 | 35,167 | 56,167 | 49,667 |

* Changes shown in GREEN