DRAFT

Programme of Work 2007 – Research Methods Group

(Work Area - Administration)

CGIAR Alignment Proposal – Action relating to the Administrative issues of the group

| ACTION |  | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 |
| --- | --- | --- | --- | --- |
| Establish joint Research Methods Group (RMG) |  | RMG functioning with approved strategic plan | RMG achieving milestones under 5 objectives and recognized within ILRI-ICRAF | RMG providing services to all partners of ESA MTP |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| Establish RMG | Meetings, website development, publicity material | $11,000 | Staff time and other costs | $89,000 |

Strategy & Objectives of the RMG that relate to the Administrative issues of the group

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Operating the RMG | - Competitive centres - Traditional narrow view of the role of biometrics both inside and outside our centres acts against engagement with research teams - Development agenda removes research focus and we need ways of blending the two - Funding support services with diminishing core - Working across 3 campuses and many outreach sites | - Single unit - Responsive to needs - Adding value not policing - Becoming part of research teams, involved in all stages and budgeted - Advertising services, keeping all staff up to date with what we do |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Establishing the RMG (Alignment activities) | Website development & publicising | - Shared (ILRI / ICRAF) website - Content and structure updated and maintained - Website widely publicised within / outside of ILRI / ICRAF - All up-to-date RM Resources available on web | Odanga Poole Buysse Other RMG staff | 2 0.5 0.75 2 days |
|  | Developing & circulating publicity material | - RMG brochure - produced and circulated - RMG business cards – 200 x each staff member | Odanga Poole | 1 0.25 |
|  | RMG group identity building | - RMG group meetings - 4 (2 x ICRAF / 2 x ILRI) - Regular seminars within group to share latest work/research (at least 4) - Finalised and agreed RMG Strategy document | All staff Odanga Poole Coe | 0.25 0.5 0.25 0.25 |
|  | RMG as recognised group | - Updated ILRI / ICRAF centre-wide info. to remove refs to ‘RSU’ or ‘Biometrics’ (e.g. contact lists, website links, finance documents) | Odanga | 0.25 |
| Operating the RMG | Monitoring & spending of the RMG core budget(s) | - ILRI & ICRAF budgets not excessively over or under-spent by end of 2007 - Spending between ILRI and ICRAF budgets showing fair and appropriate division of costs | Poole Odanga Coe | 0.5 0.5 2 days |
|  | Funding sources (charging policies) aligned, consistent & transparent to scientists | - Finalised policy on project charging within ILRI / ICRAF (in collaboration with Finance) – full implementation in 2008 - Policy for external work, including staff rates | Poole Coe | 0.25 1 day |
|  | Advertising services of RMG & other publicity generating events | - Resources for Teaching Biometrics and Research Methods (workshop) - Promoting specific aspects of RMG through seminars/discussions – (e.g. raising awareness of newly aligned policies) x 4 | Odanga Poole Other RMG staff (seminars etc.) | 1 0.25 2 days |
|  | Maintaining Time Recording summaries for all RMG staff | - Quarterly summary reports provided to RMG Advisory Group - Reports used to guide RMG staff on work areas requiring attention (e.g. more input/less input) | Odanga Poole | 0.75 0.25 |
|  | External funding sources investigated | - Capacity building in the NARS – RAPSODE funding obtained from large donor. (see ‘Training & Capacity Building’ workplan for details)* - External (to ILRI / ICRAF) consultancies – 2 (FARA = 1?) | Odanga Poole Coe | 0.25 0.25 0.25 |
|  | Professional development of RMG staff to meet new challenges in emerging areas | - Internal training courses from ‘experts’ within ILRI / ICRAF to capacity build RMG staff (e.g. R) x 2 - Courses provided by external ‘experts’ to capacity build RMG staff (e.g. Bayesian methods, problem analysis) x 2 | Odanga (admin) Coe, Poole Nagda, Taddese Matere, Ndiwa, Nyabenge, Kariuki, Taye | 0.75 0.25 /person |

* RAPSODE time shown under ‘Training & Capacity Building’ workplan

Total time (months) :

Coe (1), Odanga (7), Poole (2.75), Buysse (1), Muraya (0.5)

Nagda, Taddese, Matere, Ndiwa (0.5 + 4 days)

Taye, Kariuki, Nybenge (0.5) = 15.75months