DRAFT

Programme of Work 2007 – Research Methods Group

(Work Area – Data Analysis & Reporting)

CGIAR Alignment Proposal – Action relating to the ‘Data analysis & Reporting’ issues of the group

| ACTION |  | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 |
| --- | --- | --- | --- | --- |
| Identify research methods gaps and devise approaches to fill them |  |  | Capacity in place to provide technical support in emerging science areas needed by at least 3 project | RMG the supplier of choice for technical support in research methods among ESA projects |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| Research methods support | Publishing, staff development | $32,000 | Staff time and other costs | $42,000 |

N.B. Identical to Area for ‘Project & Study Design

Strategy & Objectives of the RMG that relate to the ‘Data Analysis & Reporting’ issues of the group

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Design and analysis | - Limited support given to outreach stations - Range of quantitative approaches needed and used is ever-growing – hard for a small group to keep up - RMG tends to be used when a problem emerges rather than as part of the team. Hence we know little about the background to the project - Lack of awareness on the part of research groups as to the potential of RMG in their work | - Being part of research teams, involved in planning, implementation, analysis and reporting - Compiling and evaluating tools and guides to help scientists - Facilitating access to newer research methods by training, developing guides,…. - Keeping lists of experts in particular methods both inside and outside the centres that can be linked to projects - Identifying emerging priority methods needed to support the research and developing the expertise necessary. - Designing statistical software policies and supporting key products - Building networks with outreach stations - Building technical skills of staff, students and partners. |

(N.B. Specific challenges & approaches relating to ‘Design’ removed in the above)

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Research methods support (Alignment activities) | Continue methods inventory & diagnosis work – combining ILRI & ICRAF needs | - Document summarising range/diversity of research areas at ILRI & ICRAF, including overlaps between organisations. Identification of research methods appropriate / needed in these areas – and where RMG can/should be involved | Coe Poole | 0.25 0.25 |
|  | Producing guides for scientists on key analysis methods | - Guides produced (or existing guides evaluated) on key statistical analysis methods and available on-line for researchers x 1/person. Back-stopping from RMG staff.* - Guides produced (if not already existing) on specific analysis methods in RMG supported statistical packages* | Odanga (pub’n) Matere Coe, Poole Nagda, Taddese Ndiwa | 0.5 0.5 0.25 |
|  | Professional development of RMG staff to meet new challenges in emerging areas | See ‘Admin’ Workplan |  |  |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Analysis & Reporting | Analysis & reporting support to ILRI & ICRAF projects | - Staff members providing analysis & reporting support to research teams at ILRI & ICRAF (≥ 3 teams / person) | Coe Poole Nagda, Matere Taddese Ndiwa | 0.5 1 3.75 4 1.5 |
|  | Achieving closer links to research teams (i.e. involved in planning, implementation, analysis & reporting) | - RMG staff linked to specific project budgets for 2008 x 1/person - Recognition of RMG input by project leaders – how to measure? | Coe, Poole, Nagda, Taddese, Matere, Ndiwa | N / A |
|  | Compiling & evaluating tools / guides to help scientists in (design &) analysis | See 2nd Task under ‘Research methods support’ |  |  |
|  | Facilitating access to newer research methods by training, developing guides | See 2nd Task under ‘Research methods support’ and final section |  |  |
|  | Maintaining list of ‘experts’ in particular methods, inside & outside of ILRI / ICRAF – link to projects | - Database of ‘experts’ in particular methods – kept updated as staff members arrive/depart. Formatted & web enabled. | Odanga All staff (input) | 0.5 |
|  | Identifying emerging priority methods to support research & developing expertise necessary | See 1st & 3rd tasks under ‘Research methods support’ |  |  |
|  | Designing & implementing statistical software policies & supporting key products | - ILRI / ICRAF joint software policy available – including various levels of support available from RMG - Alignment of software licenses between ILRI – Nairobi, ICRAF – Nairobi, ILRI – Addis & outreach stations | Nagda Ndiwa Taddese | 0.25 0.25 0.25 |
|  | Building networks with key ICRAF & ILRI outreach stations | - Visits to key outreach stations (ILRI – India, ICRAF – Indonesia, W.Africa) to provide advice (analysis, DM, training), facilitate access to a range of research methods, encourage remote communications/support x 1/person | Coe Poole Nagda Taddese | 0.5 0.5 0.5 0.5 |
|  | Building technical skills of staff, students & partners (design, analysis & reporting) | See ‘Training & Capacity Building’ Workplan & ‘Admin’ Workplan for website development. |  |  |
| * Possible areas include: - Meta-analysis (combined animal trials) - Survey design & analysis (epidemiological, socio-economic/social, evaluation of ‘development’ actions) - Presentation of genetic diversity data (see link in GIS) - Linking multi-scale empirical data & models - Bayesian networks and post-normal science – modelling, describing and using conflicting uncertain information. - Methods for qualitative data – should have capabilities to explain alternative approaches & make recommendations. Should get familiar with WinKAT. - Spatial analysis & modelling (link to GIS) - Expanding genetics research methods – including population genetics, microarray data - Analysis methods in R – e.g. QTL, mixed modelling, survival analysis |  |  |  |  |

Total time (months):

Coe (1.5), Poole (2), Nagda (4.75), Taddese (5), Matere (4.25), Ndiwa (2), Odanga (1) = 21 months