DRAFT

Programme of Work 2007 – Research Methods Group

(Work Area – Data Management)

CGIAR Alignment Proposal – Action relating to the ‘Data Management’ issues of the group

| ACTION |  | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 |
| --- | --- | --- | --- | --- |
| Design and implement research data management strategies |  | Aligned data management policies adopted in both ILRI and ICRAF | Priority projects in ICRAF and ILRI fully implementing data management policies | ESA MTP projects using best practice for research data management |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| Research data management | Workshops, travel, consultants | $25,000 | Staff time and other costs | $84,000 |

| Extent to which 2007 milestone met | Deficiencies | Reasons/comments | Actions for 2008 |
| --- | --- | --- | --- |
| Draft policy document under review. |  |  | Update draft based on inputs from reviewers. Implement policy by:- (a) Training the trainers (i.e. RMG staff, public awareness officers). (b) Create awareness through workshops and seminars (for data curators). © Providing resources for supporting the policy |

Strategy & Objectives of the RMG that relate to the ‘Data Management’ issues of the group

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Research data management | - Value of research data limited by not maintaining high quality archives - Inefficient data processing due to poor understanding of management needs - Data and other research documents not linked - Data vulnerable due to poor documentation, inadequate backup, few people who know about any dataset,… - Projects with multiple partners often have no clear data ownership and sharing policy - Technical tools to help in RDM not known or adopted - All the above compounded by distributed research sites and teams | - Develop aligned data management, ownership and access policies - Assist all projects with integrated data management strategies that meet immediate and long term needs - Provide tools and approaches to help technicians, scientists and managers assess and improve their data management - Help centres establish and maintain long term research data archives - Build mechanisms for allowing outreach scientists to be fully integrated into data management practice - Create means of monitoring use of our data and getting feedback |

| Changed Weaknesses and Threats | Changed strengths and opportunities |
| --- | --- |
|  | Increased awareness of the problem |

| Area | Changed: Key Challenges | Changed: Approaches |
| --- | --- | --- |
| Spatial | - good and bad practice hidden - large backlog of data - fraud is hardly talked about |  |

| Area | Task Description | Expected Outputs for 2007 | Achievements | Deficiencies and reasons |
| --- | --- | --- | --- | --- |
| RDM (Alignment activities) | Design and implement research data management strategies | - Aligned data management policy (quality, efficiency, preservation) produced. - Technical implementation & documentation of aligned data management policy – 2 workshops (ILRI & ICRAF) for staff to review & comment. - Travel to key other centres to implement system x 2 trips | - Draft version, under review by ILRI ICRAF staff. | Definition of a project since policy builds on it some experiments being longer than projects; Emails as data; Doubts whether the model we suggest is really practical – want to see it demonstrated; automated archiving?? |

| Area | Task Description | Expected Outputs for 2007 | Achievements | Deficiencies and reasons |
| --- | --- | --- | --- | --- |
| Research Data Management | Assist all projects with integrated data management strategies that meet immediate and long term needs | - Integrated data management strategies designed & implemented for ≥ 4 research teams. | 1. Attempted to archive the data from BT02 (Duncan Mwangi) 2. Conceptual design of the Investigations database (Tony’s ideas on integrated research planning, monitoring and reporting) 3. Designed and presented a strategy for the SSA-CP | (1a) Method assumption failed – that people use folders and meaningful names to organize data. Well, Mwangi had 3000 files in a single folder, My documents!. (1b) underestimating demand for time 2. Not yet implemented because of time constraints. 3. No follow-up / continuing support 4. Input not requested from projects at ILRI? |
|  | Tools and approaches to help technicians, scientists and managers assess and improve their data management | - Data Publishing guide produced for ILRI / ICRAF staff & assistance provided on its use x 2 workshops. - Guide to data management in R – or evaluation & recommendation on alternative materials. | 1. Student helped to supplement the Data Publisher Guide (Cathy Garlik) with a Checklist that would be useful for data curators 2a. Identified resources in the internet and circulated to RMG staff based in ILRI campus 2b. Client-Server Paradigm for Managing Research Data: individual writing workshop report | 1. Data publisher system has not circulated hence the manual has not been used, since the policy has not been implemented. – Doesn’t need the policy to implement the system, but needs support by all DM and Stats staff 2. No feedback or follow-up |
|  | Help centres establish and maintain long term research data archives | - Similar to Output in Task 1 above – but focus on data archives, staff leaving/arriving. | Data From long term projects archived into a centralized repository of spatial data (from Russ Kruska) | Difficult to remember the unrecorded details. |
|  | Create means of monitoring use of our data and getting feedback to identify emerging problems | See under implementation of data management policy – more follow-up in 2008. |  | The success of this would have been depended on the success of implementation of RDM. |
|  | Support to ILRI / ICRAF projects on database design & use | 1. Input into ≥ 4 projects (per location) | 1. Following databases were designed a. FARA b. SCALES c. BECA d. Indigenous fruit database e. BTO2 TB database. 2. Supervised development of SLP & CBPP database 3. Assisted in designing the IDEAL database. | 1a. The way the data was captured for FARA project was not suitable for direct loading into a database. Why? 1c. Since it was interactive there were always new ideas being incorporated and thus made it difficult to complete. 1d. Batch correction of errors was tedious. 2. SLP – little progress so far as lacking detail from OPL. Would appreciate support from RDM specialists in the group to RMG non-RDM specialists who are being asked for support in these areas. |