DRAFT

Programme of Work 2007 – Research Methods Group

(Work Area – Data Management)

CGIAR Alignment Proposal – Action relating to the ‘Data Management’ issues of the group

| ACTION |  | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 |
| --- | --- | --- | --- | --- |
| Design and implement research data management strategies |  | Aligned data management policies adopted in both ILRI and ICRAF | Priority projects in ICRAF and ILRI fully implementing data management policies | ESA MTP projects using best practice for research data management |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| Research data management | Workshops, travel, consultants | $25,000 | Staff time and other costs | $84,000 |

Strategy & Objectives of the RMG that relate to the ‘Data Management’ issues of the group

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Research data management | - Value of research data limited by not maintaining high quality archives - Inefficient data processing due to poor understanding of management needs - Data and other research documents not linked - Data vulnerable due to poor documentation, inadequate backup, few people who know about any dataset,… - Projects with multiple partners often have no clear data ownership and sharing policy - Technical tools to help in RDM not known or adopted - All the above compounded by distributed research sites and teams | - Develop aligned data management, ownership and access policies - Assist all projects with integrated data management strategies that meet immediate and long term needs - Provide tools and approaches to help technicians, scientists and managers assess and improve their data management - Help centres establish and maintain long term research data archives - Build mechanisms for allowing outreach scientists to be fully integrated into data management practice - Create means of monitoring use of our data and getting feedback |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| RDM (Alignment activities) | Design and implement research data management strategies | - Aligned data management policy (quality, efficiency, preservation) produced. - Draft version, resulting from merging older versions from ICRAF & ILRI, initial inputs from Nicholas and latter fine-tuning by Jane and Ric - Document under review by ILRI ICRAF staff. - So far, most inputs from ILRI; only one response from ICRAF! - Major comment is that it is a useful step - Key worries are: Definition of a project since policy builds on it; some experiments being longer than projects; Emails as data; Doubts whether the model we suggest is really practical – want to see it demonstrated; automated archiving - Technical implementation & documentation of aligned data management policy – 2 workshops (ILRI & ICRAF) for staff to review & comment. - 2 seminars held, both at ICRAF and ILRI - At ILRI, attendants were potential data curators - At ICRAF, attendants were project leaders (consequence of Tony’s input) - Travel to key other centres to implement system x 2 trips - Jane presented seminar at Addis (provided lots of feedback) | Muraya Ndiwa Coe Poole | 3 1.5 0.5 0.25 |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Research Data Management | Assist all projects with integrated data management strategies that meet immediate and long term needs | - Integrated data management strategies designed & implemented for ≥ 4 research teams. - Designed and presented a strategy for the SSA-CP. A bit apprehensive about the whole program - Attempts to use ‘Rapid metadata methods’ strategy on Duncan Mwangi’s type of data was less successful for 2 reasons (1) Method assumption failed – that people use folders and meaningful names to organize data. Well, Mwangi had 3000 files in a single folder, My documents!. (2) underestimating demand for time – difficult to get a contiguous week for both me and Sonal - Ideas on Tony’s Investigations database (as a means for integrated research planning, monitoring and reporting) have not progressed beyond conceptual design | Muraya Ndiwa | 2 0.5 |
|  | Tools and approaches to help technicians, scientists and managers assess and improve their data management | - Data Publishing guide produced for ILRI / ICRAF staff & assistance provided on its use x 2 workshops. - Student helped to supplement the Guide by Cathy with a Checklist that would be useful for data curators - Guide to data management in R – or evaluation & recommendation on alternative materials. - The closest we came to document resulting from the last writeshop ‘Client-Server Paradigm for Managing Research Data: individual writing report in which we referred to R as one of the data clients | Muraya Ndiwa Poole | 2 0.5 0.25 |
|  | Help centres establish and maintain long term research data archives | - Similar to Output in Task 1 above – but focus on data archives, staff leaving/arriving. - Have developed a system, with assistance from another student, Karin, (a) for acquiring quality metadata seamlessly by data originators (b) transmitting them over the internet to a central location managed by data curators/archivist. - Will be the basis of a ‘hands on training’ on the Data understandability chapter of the RDM policy | Muraya | 1 |
|  | Create means of monitoring use of our data and getting feedback to identify emerging problems | See under implementation of data management policy – more follow-up in 2008. |  |  |
|  | Support to ILRI / ICRAF projects on database design & use | 1. Input into ≥ 4 projects (per location) - Nicholas has had most input on this e.g. Beca case - Assistance to Panwell | Muraya Ndiwa | 1 2 |

Total time (months):

Coe (0.5), Poole (0.5), Muraya (9), Ndiwa (4.5) = 14.5 months