DRAFT

Programme of Work 2007 – Research Methods Group

(Work Area – Training & Capacity Building)

CGIAR Alignment Proposal – Action relating to the ‘Training & Capacity Building’ issues of the group

| ACTION |  | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 |
| --- | --- | --- | --- | --- |
| Build capacity for quality research services among partners in ESA |  |  | Strategy devised and funding proposals prepared | Funding secures and implementation started |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| Research quality capacity in ESA | Regional consultation, planning meetings , proposal development | $42,000 | Staff and other costs | $54,000 |

Strategy & Objectives of the RMG that relate to the ‘Training & Capacity Building’ issues of the group

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Regional Capacity | - Capacity of NARS to conceive and implement useful research often limited by experience and resources - Universities use traditional teaching methods that do not develop innovation and critical thinking - Resources for using newer methods not known or used - Capacity building in NARS often limited to demanding provision of training courses and the perceived training needs do not always match the real needs | - Not just focusing on statistics and data management, but covering the whole research process from initial problem analysis to publication of research results and their impact. - Also including topics such as gender, ethics, fraud and misconduct, research as a social process - Not only working with biometricians, lecturers and supervisors, but also directly with a mix of researchers, students and relevant staff of government departments and development NGO’s - Not going into the politics of changing the educational system, university reforms etc. but trying to motivate individuals how to do things differently within the “lousy system” - When working with lecturers and supervisors, stimulate them to think about different ways of teaching and interacting with students - Distribute training and teaching resources in the most appropriate and cost-effective way (as much as possible for free) so that others can use them in their teaching and training. - Also distribute training and teaching resources that exist already but are not widely known. |
| Design & Analysis |  | - Building technical skills of staff, students and partners. - Facilitating access to newer research methods by training, developing guides,…. |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Research quality capacity in ESA (Alignment activities) | Complete, publish and disseminate key paper on teaching research methods | 1. Output as Task Description – “Towards a conceptual framework for teaching research methods” | Buysse Coe | 0.25 0.25 |
|  | Regional consultation and planning meetings and an education consultant to prepare a major proposal that will continue after end of VVOB project | 1. RAPSODE project developed through consultation with regional Universities and NARS. Project proposal sent to major donor | Buysse Coe Poole | 1.5 0.25 0.25 |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Regional Capacity | Capacity building to regional libraries | - Restoration of INERA Mulungu library - Books supplied to KEFRI and/or Kisangani library | Buysse | 0.25 |
|  | Training & activities for KEFRI | - Training workshops – representation as Resource person(s) - Publication of technical notes x 3 | Buysse KEFRI partners | 3 |
|  | Induction Training Workshops | See “Research Quality Systems” Workplan |  |  |
|  | Distribution of training and teaching resources | - Update & maintain research methods resources – website & CD (> 2000 CD’s to be distributed)+ - Development of “Biometrics & Research Methods Teaching Resource”. Options: further case studies, analysis in R - Update manuals for GenStat Discovery 3rd Edition | Buysse Odanga Poole Matere Ndiwa Taddese Researcher attachments | 3.5 1.5 0.25 1 0.5 0.5 |
| Training | Building technical skills of staff, students & partners (design, analysis & reporting) | See ‘Analysis & Reporting’ Workplan and ‘Project & Study Design’ Workplan |  |  |
|  | Facilitating access to newer research methods by training, developing guides,…. | - 2 internal well run courses at ILRI / ICRAF – one charged to cover cost, one free (to estimate potential for internal charging).* - Specialised training courses given ‘on demand’ x 2 (e.g. STATA course to ILRI Theme 3 project) | Matere Nagda Ndiwa Taddese Coe Poole | 2 2 0.5 1 0.5 0.5 |

* Possible courses: Introduction to R, …

+ Time for work on website included in Admin workplan (Alignment activities)

Total time (months):

Coe (1), Buysse (8.5), Poole (1), Nagda (2), Taddese (1.5), Matere (3), Ndiwa (1), Odanga (1.5) = 19.5 months